## Overview
SocialTech Project Planning | Sprint-based project management plan for 1 solo developer
Prepared Date | 2026-05-02
Project Type | Personal project / backend-first social platform
Development Capacity | 1 developer, 3-4 hours per day, around 18 hours per 1-week sprint
Sprint Cadence | 1 sprint = 1 week. Goal is to keep planning lightweight and releasable every 1-2 sprints.
Planning Principle | Prioritize usable slices: foundation -> auth -> content -> social interaction -> moderation -> release hardening
Current Baseline | Codebase already shows partial implementation for auth, user, article/post, email, media storage, and database schema for community/comment/vote/report.
Success Criteria | Each sprint should end with one testable outcome, minimal regression, and short technical notes for the next sprint.
Release Strategy | Internal alpha after Sprint 4, closed beta after Sprint 7, personal MVP release after Sprint 9.

## Master Plan
ID | Epic / Module | Scope Summary | Priority | Status | Target Sprint | Est. Effort | Note
EP01 | Foundation & Environment | Project structure, config, database migration, media storage, exception handling, basic logging, local runbook | High | Partial | Sprint 1 | 12-16h | Stabilize existing base before new features
EP02 | Authentication & Account | Register, login, forgot/reset password, token policy, validation, basic security rules | High | Partial | Sprint 1-2 | 20-24h | Login exists; complete account lifecycle
EP03 | User Profile & Follow | Profile view/update, avatar upload, follow/unfollow, follower list, privacy rules | High | Partial | Sprint 2 | 16-20h | Most APIs exist but need finishing and testing
EP04 | Post / Article Core | Create/update/delete post, upload attachments, validation, ownership checks, post detail | High | Partial | Sprint 3 | 18-24h | Core CRUD exists; add read flows and cleanup
EP05 | Feed, Listing & Tag | Home feed, user posts, community posts, tag binding, pagination, sorting | High | Planned | Sprint 4 | 18-22h | Needed to make content actually consumable
EP06 | Community Management | Create community, update community, membership join/leave, rules, owner/mod roles | Medium | Schema Ready | Sprint 5 | 20-26h | DB and repositories exist, API flow still missing
EP07 | Comment & Reply | Comment CRUD, nested replies, locking rules, pagination for comment tree | High | Schema Ready | Sprint 6 | 20-24h | Important for social interaction
EP08 | Vote / Engagement | Vote for posts/comments, score update, duplicate prevention, basic counters | Medium | Schema Ready | Sprint 6 | 10-14h | Can be bundled with comments
EP09 | Report & Moderation | Report post/comment, queue view, status handling, moderator action record | Medium | Schema Ready | Sprint 7 | 18-22h | Essential before public usage
EP10 | Notification & Email | Welcome/reset emails, event hooks, async handling, error visibility | Medium | Partial | Sprint 7 | 10-14h | Email pieces exist; consolidate behavior
EP11 | Quality, Test & Deployment | Integration checks, smoke tests, Docker flow, seed data, release checklist | High | Planned | Sprint 8-9 | 20-28h | Needed to turn project into maintainable MVP

## Sprint Plan
Sprint | Duration | Capacity | Sprint Goal | Planned Deliverables | Release Gate
Sprint 1 | 1 week | 18h | Stabilize base project and close account flow gaps | Review environment setup, clean config, confirm migration, finish register/forgot/reset flow, add auth validation/error handling | Can create account and recover password
Sprint 2 | 1 week | 18h | Finish user profile slice | Profile API verification, avatar update, follow/unfollow, follower listing, privacy rule review, basic test scenarios | User profile flow works end-to-end
Sprint 3 | 1 week | 18h | Make posting flow reliable | Refine create/update/delete post, file upload constraints, ownership/security checks, add post detail/read endpoint, error cases | A user can publish and manage own posts
Sprint 4 | 1 week | 18h | Make content browsable | Implement feed/list APIs, pagination, filter by user/community, tag attachment or tag query path, simple sorting rules | Internal alpha usable for reading posts
Sprint 5 | 1 week | 18h | Open community feature | Create/edit community, join/leave community, membership role basics, community rules CRUD lite, community detail/list API | Community slice works with posts
Sprint 6 | 1 week | 18h | Add interaction depth | Comment/reply APIs, nested reply policy, post vote/comment vote, score update logic, duplicate vote prevention | Users can discuss and react to content
Sprint 7 | 1 week | 18h | Add trust and moderation controls | Report API, moderation queue basic endpoints, assign/status update, email/event cleanup, audit-friendly response shape | Closed beta baseline is safe enough
Sprint 8 | 1 week | 18h | Harden the MVP | Integration test checklist, performance review for key queries, Docker/local deployment polish, seed/demo data, API documentation cleanup | MVP candidate build ready
Sprint 9 | 1 week | 18h | Buffer sprint for bug fixing and release | Fix defects from test usage, polish gaps, simplify backlog, prepare release note and next-phase backlog | Personal MVP release

## Task Detail
Sprint | Task ID | Feature | Task Type | Est. Hours | Priority | Status | Definition of Done
Sprint 1 | S1-01 | Environment review | Tech | 3h | High | Planned | App runs locally with clear config and migration steps documented
Sprint 1 | S1-02 | Register flow | Feature | 5h | High | Planned | User can create account with validation and duplicate checks
Sprint 1 | S1-03 | Forgot/reset password | Feature | 6h | High | Planned | Reset token flow works and invalid token cases are handled
Sprint 1 | S1-04 | Auth error handling | Tech | 4h | Medium | Planned | API returns stable error shape for auth-related failures
Sprint 2 | S2-01 | Profile read/update | Feature | 7h | High | Planned | Profile data can be viewed and updated including avatar path
Sprint 2 | S2-02 | Follow/unfollow | Feature | 5h | High | Planned | Follow state updates correctly and duplicate action is blocked
Sprint 2 | S2-03 | Follower listing | Feature | 4h | Medium | Planned | Follower/following list supports paging and ownership rules
Sprint 2 | S2-04 | Profile smoke test | QA | 2h | Medium | Planned | Main profile flows are manually verified with notes
Sprint 3 | S3-01 | Post CRUD stabilization | Feature | 8h | High | Planned | Author can create, edit, delete own post without broken media linkage
Sprint 3 | S3-02 | Attachment handling | Tech | 4h | High | Planned | File type/size rules are enforced and bad uploads fail safely
Sprint 3 | S3-03 | Post detail endpoint | Feature | 4h | High | Planned | Single post can be retrieved with core metadata
Sprint 3 | S3-04 | Post regression pass | QA | 2h | Medium | Planned | Existing post APIs still behave correctly after changes
Sprint 4 | S4-01 | Feed endpoint | Feature | 6h | High | Planned | Client can retrieve paginated feed ordered by defined rule
Sprint 4 | S4-02 | User/community post list | Feature | 5h | High | Planned | Posts can be filtered by author or community
Sprint 4 | S4-03 | Tag linkage or query | Feature | 4h | Medium | Planned | Posts can be associated with or queried by tags
Sprint 4 | S4-04 | Alpha review | QA | 3h | Medium | Planned | Core browse/post journey is manually testable end-to-end
Sprint 5 | S5-01 | Create/edit community | Feature | 7h | High | Planned | Community owner can create and update a community profile
Sprint 5 | S5-02 | Membership flow | Feature | 5h | High | Planned | User can join/leave community and state is persisted
Sprint 5 | S5-03 | Community rules lite | Feature | 4h | Medium | Planned | Owner can manage a small ordered list of rules
Sprint 5 | S5-04 | Community list/detail | Feature | 2h | Medium | Planned | Community can be discovered and viewed from API
Sprint 6 | S6-01 | Comment CRUD | Feature | 7h | High | Planned | Users can add/edit/delete comments under allowed rules
Sprint 6 | S6-02 | Reply/nesting | Feature | 4h | High | Planned | Replies support parent linkage and depth rule consistently
Sprint 6 | S6-03 | Post/comment voting | Feature | 5h | Medium | Planned | Single user cannot create duplicate vote and score reflects latest state
Sprint 6 | S6-04 | Interaction smoke test | QA | 2h | Medium | Planned | Discuss/react flow works on representative scenarios
Sprint 7 | S7-01 | Report content | Feature | 5h | High | Planned | User can report post/comment with reason and details
Sprint 7 | S7-02 | Moderation queue | Feature | 6h | High | Planned | Moderator can list and change report status
Sprint 7 | S7-03 | Notification/email cleanup | Tech | 4h | Medium | Planned | Mail/event behavior is stable for main account/report triggers
Sprint 7 | S7-04 | Beta review | QA | 3h | Medium | Planned | Moderation-related risks are identified and logged
Sprint 8 | S8-01 | API checklist | QA | 5h | High | Planned | Critical APIs have explicit smoke/regression checklist
Sprint 8 | S8-02 | Performance pass | Tech | 4h | Medium | Planned | Main listing queries are reviewed and obvious bottlenecks addressed
Sprint 8 | S8-03 | Docker and deployment polish | DevOps | 5h | High | Planned | Local deploy path is reproducible using concise steps
Sprint 8 | S8-04 | Seed/demo data | Tech | 4h | Medium | Planned | There is enough demo data to validate core product flow
Sprint 9 | S9-01 | Bug fixing buffer | Bugfix | 8h | High | Planned | Priority defects from MVP candidate are resolved
Sprint 9 | S9-02 | Backlog trim | PM | 4h | Medium | Planned | Post-MVP backlog is prioritized into next-phase themes
Sprint 9 | S9-03 | Release note | PM | 2h | Low | Planned | Release scope and known limitations are written down
Sprint 9 | S9-04 | Final verification | QA | 4h | High | Planned | MVP release candidate passes the final manual checklist

## Milestones
Milestone | Target Sprint | Expected Date | Definition | Status
M1 - Foundation Ready | Sprint 1 | Week 1 | Core environment and account flow are stable enough for continued feature development | Planned
M2 - User Slice Ready | Sprint 2 | Week 2 | A user can register, login, manage profile, and follow another user | Planned
M3 - Content Slice Ready | Sprint 4 | Week 4 | Users can publish content and browse a basic feed/listing | Planned
M4 - Community Interaction Ready | Sprint 6 | Week 6 | Communities, comments, replies, and voting exist in usable form | Planned
M5 - Closed Beta Ready | Sprint 7 | Week 7 | Moderation and trust controls are available for controlled usage | Planned
M6 - Personal MVP Release | Sprint 9 | Week 9 | Project is releasable for personal MVP usage with known limitations documented | Planned